## Sheet1
[20 empty] | Final Ghanam |  |  | Final Jatai
Srl No | PraSnam | Padam Copied | Process Parameters like PS, Pre, PGS | TTD Jatai Hearing 1 | Ghanam Hearing 1 | Basic Checks | JM,JD,GD Ref | update GS | Generate Control Stats | Verify Stats | Final Review | Generate Ghanam & Jatai | First Review | Ghanam Hearing Final | Mark Corrections | Match Ghanam and Jatai files | Feedback for Program | update Excel Template | Re Run Program | Sanskrit | Malayalam | Tamil | Sanskrit | Malayalam | Tamil
1 | TS 1.1 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Yes
2 | TS 1.2 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Yes
3 | TS 1.3 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Yes
4 | TS 1.4 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Yes
5 | TS 1.5 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Yes
6 | TS 1.6 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Yes
7 | TS 1.7 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Yes
8 | TS 1.8 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Yes
9 | TS 2.1 | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | [5 empty] | 2022-03-29 | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-29 | 2022-03-30
10 | TS 2.2 | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | 2022-04-16 | 2022-04-16 | 2022-04-17 | 2022-04-16 | 2022-04-16 | 2022-04-17
11 | TS 2.3 | Yes | Yes | Yes |  | Yes | Yes | Yes | Yes | Yes | Yes | 2022-04-23 | Yes | Yes | Yes | Yes | Yes | Yes |  | 2022-05-10 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-12 | 2022-05-12
12 | TS 2.4 | Yes | Yes | Yes |  | Yes
13 | TS 2.5 | Yes | Yes | Yes |  | Yes
14 | TS 2.6 | Yes | Yes | Yes |  | Yes
15 | TS 3.1 | Yes | Yes | Yes | 2022-04-05 | Yes | Yes | Yes
16 | TS 3.2 | Yes | Yes | Yes | 2022-04-08 | Yes | Yes | Yes
17 | TS 3.3 | Yes | Yes | Yes | 2022-04-10 | Yes | Yes | Yes
18 | TS 3.4 | Yes | Yes | Yes | 2022-04-13 | Yes | Yes | Yes
19 | TS 3.5 | Yes | Yes | Yes | 2022-04-14 | Yes | Yes | Yes
20 | TS 4.1 | Yes | Yes | Yes | 2022-03-29 | Yes
21 | TS 4.2 | Yes | Yes | Yes | 2022-04-01 | Yes
22 | TS 4.3 | Yes | Yes | Yes | 2022-04-16 | Yes
23 | TS 4.4 | Yes | Yes | Yes | 2022-04-18 | Yes
24 | TS 4.5 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
25 | TS 4.6 | Yes | Yes | Yes | 2022-04-20 | Yes
26 | TS 4.7 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
27 | TS 5.1 | Yes | Yes | 2022-04-27 | 2022-04-30 |  |  | Yes
28 | TS 5.2 | Yes | Yes | 2022-05-04 | 2022-05-05
29 | TS 5.3 | Yes | Yes | 2022-05-06
30 | TS 5.4 | Yes | Yes | 2022-05-08
31 | TS 5.5 | Yes | Yes | 2022-05-09
32 | TS 5.6 | Yes | Yes | 2022-05-10
33 | TS 5.7 | Yes | Yes | 2022-05-11
34 | TS 6.1 | Yes | Yes
35 | TS 6.2 | Yes | Yes
36 | TS 6.3 | Yes | Yes
37 | TS 6.4 | Yes | Yes
38 | TS 6.5 | Yes | Yes
39 | TS 6.6 | Yes | Yes
40 | TS 7.1 | Yes | Yes
41 | TS 7.2 | Yes | Yes
42 | TS 7.3 | Yes | Yes
43 | TS 7.4 | Yes | Yes
44 | TS 7.5 | Yes | Yes